## Defect Log (Sprint1)
Schaumburg Marketplace Defect Log (Sprint 1)
Defect ID | Defect Description | Module | Severity | Status | Assigned To | Detected By | Detected Date | Test Case Id | Comments
001 | Clicking on "Buy or Sell" text does not redirect to the correct page. Redirects to the contact page instead. | Services | High | Assigned | SMP Dev | Ana | 2024-10-24 | TCSR_17 | Link redirects incorrectly; further investigation needed.
002 | Clicking on "Email Marketing" text does not load the page successfully. Redirects to the contact page instead. | Services | High | Assigned | SMP Dev | Ana | 2024-10-24 | TCSR_21 | Link redirects incorrectly; further investigation needed.
003 | Clicking on "Website Design" title text does not load the page successfully. Redirects to the contact page instead. | Services | High | Assigned | SMP Dev | Ana | 2024-10-25 | TCSR_37 | Link redirects incorrectly; further investigation needed.
004 | Form does not validate all fields correctly when invalid data is provided; only shows error for email field. | Contact Us | Medium | Assigned | SMP Dev | Ana | 2024-10-25 | TCEM_10_9 | Form did not submit; displayed error for email only.
005 | Form allows submission with a valid email but incorrect other fields, which should not be the case. | Contact Us | Medium | Assigned | SMP Dev | Ana | 2024-10-26 | TCEM_10_11 | Incorrect submission behavior; valid email should not bypass validation.
006 | Map fails to locate a valid address; displays error message indicating it cannot find the address. | Map Functionality | High | Assigned | SMP Dev | Ana | 2024-10-27 | TCEM_10_13 | Map functionality is not working as expected.
007 | Clicking the Checkout button results in an error message and does not allow proceeding to the checkout page. | Shopping Cart | High | Assigned | SMP Dev | Ana | 2024-10-27 | TCSC_022 | Checkout functionality is not working as intended,
008 | Verify the message submission with special characters. Name: "!@#$%^&()" Email: "!@#$%^&()" Message: "!@#$%^&*()" | Message Icon | High | Assigned | SMP Dev | Ana | 2024-10-28 | TCFT_029 | Message submitted successfully despite invalid characters; bug needs fixing.
009 | 2 'is any' available in the dropdown | Offers | Low | Assigned | SMP Dev | Lei | 2024-10-28 | TCOF_01_011 TCOF_01_012
010 | Select' is listed in the businesses and displayed on the bar once selected | Offers | High | Assigned | SMP Dev | Lei | 2024-10-28 | TCOF_01_011 TCOF_01_012
011 | Not sorted alphabetically, Services should be after Retail | Business Directory - Browse | Low | Assigned | SMP Dev | Lei | 2024-10-28 | TCBD_01_011 TCBD_01_012
012 | Flyers field are not displaying or defaulting correctly as per Membership Level once Silver is selected | BO Homepage - Membership | High | Assigned | SMP Dev | Lei | 2024-10-29 | TCBD_03_001 TCBD_03_002
013 | Shopping Cart is not cleared for new Business Owner adding new business for the first time | BO Homepage | High | Assigned | SMP Dev | Lei | 2024-10-29 | TCBD_03_001 TCBD_03_002
014 | Incorrrect details displayed on Shopping Cart page | BO Homepage - Shopping Cart | High | Open | SMP Dev | Lei | 2024-10-29 | TCBD_03_001 TCBD_03_002
015 | User is redirected to a separate Knack Search Jobs page instead of the login or sign up for new account page within the original test data page | Jobs - Apply for Job | High | Open | SMP Dev | Randy | 2024-10-29 | TC-AFJ-01
016 | Once you register for Event it does not have any option for payment | Events | High | Open | SMP Dev | Shreya | 2024-10-30 | TCE_70

## Sheet2
| High | Medium | Low | Total
Assigned | 9 | 2 | 2 | 13
Open | 3 |  |  | 3
Closed | 0 | 0 | 0 | 0