## Search Jobs
|  |  | Project Name | Schaumburg Market Place |  | Test Designed Date | 2024-10-24
|  |  | Module Name | Jobs |  | Test Executed By | Randy
|  |  | Test Designed By | Randy |  | Test Executed Date | 2024-11-01
Pre-condition
Dependencies:
Test Priority
ID | Test Description | Test Data | Enviroment | Test Steps | Expected Result | Actual Result | Status | Comment
TCJ-01 | Verify that the jobs page loads successfully | https://www.schaumburgmarketplace.net/jobs | Google Chrome Desktop | 1. Open the Schuamburg Market Place Webisite in Chrome 2. Navigate to the jobs page | The jobs page should load fully, displaying the text and images | The jobs page dispalyed successfully, with the correct text and images | Pass | Page loaded as expected
TCJ-02 | Verify that the jobs page loads successfully | https://www.schaumburgmarketplace.net/jobs | IE Browser | 1. Open the Schuamburg Market Place Webisite in Explorer 2. Navigate to the jobs page | The jobs page should load fully, displaying the text and images | The jobs page dispalyed successfully, with the correct text and images | Pass | Page loaded as expected
TCJ-KS-03 | Verify that keyword search returns relevant job listings | Keyword/phrase "Quality Assurance " | Google Chrome Browser | 1. Navigate to the search jobs page 2. Enter "Quality Assurance " in the Keyword search field 3. Click on the search button | Job listings containing " Quality Assurance "should be displayed | "Quality Assurance" Jobs display successfully | Pass | Keyword functionality works as expected
TCJ-KS-04 | Verify that keyword search returns relevant job listings | Keyword/phrase "Quality Assurance " | IE Browser | 1. Navigate to the serach jobs page 2. Enter "Quality Assurance " in the Keyword search field 3. Click on the search button | Job listings containing " Quality Assurance "should be displayed | "Quality Assurance" Jobs display successfully | Pass | Keyword functionality works as expected
TC-JC-05 | Verify that Job Category search returns relevant job listings | Job Category: "Networking" | Google Chrome Browser | 1. Navigate to the serach jobs page 2. select "Networking" from the job category drop down menu 3. Click on the search button | Only job listings under "Networking" category should be displayed | Only "Networking" Jobs displayed successfully | Pass | Ensure categories are accuratley populated
TC-JC-06 | Verify that Job Category search returns relevant job listings | Job Category: "Networking" | IE Browser | 1. Navigate to the serach jobs page 2. select "Networking" from the job category drop down menu 3. Click on the search button | Only job listings under "Networking" category should be displayed | Only "Networking" Jobs displayed successfully | Pass | Ensure that categories are accuratley populated
TC-JC-07 | Verify that Job Category search returns relevant job listings | Job Category: "Management " | Google Chrome Browser | 1. Navigate to the serach jobs page 2. select "Management " from the job category drop down menu 3. Click on the search button | Only job listings under "Management " category should be displayed | Only "Management " Jobs displayed successfully | Pass | Ensure that categories are accuratley populated
TC-JC-08 | Verify that Job Category search returns relevant job listings | Job Category: "Management " | IE Browser | 1. Navigate to the serach jobs page 2. select "Management " from the job category drop down menu 3. Click on the search button | Only job listings under "Management " category should be displayed | Only "Management " Jobs displayed successfully | Pass | Ensure that categories are accuratley populated
TC-JC-09 | Verify that Job Category search returns relevant job listings | Job category "Legal" | Google Chrome Browser | 1. Navigate to the serach jobs page 2. select "Legal " from the job category drop down menu 3. Click on the search button | Only job listings under "Legal" " category should be displayed | "No Results Found" displayed successfully | Pass | This job category generated a "No Results Found" message
TC-JC-10 | Verify that Job Category search returns relevant job listings | Job Cataegory "Legal" | IE Browser | 1. Navigate to the serach jobs page 2. select "Legal " from the job category drop down menu 3. Click on the search button | Only job listings under "Legal" " category should be displayed | "No Results Found" displayed successfully | Pass | This job category generated a "No Results Found" message
TC-JC-11 | Verify that Job Category search returns relevant job listings | Job Category "Business" | Google Chrome Browser | 1. Navigate to the serach jobs page 2. select "Business" from the job category drop down menu 3. Click on the search button | Only job listings under "Busness " category should be displayed | Only "Business" Jobs displayed successfully | Pass | Ensure that categories are accuratley populated
TC-JC-12 | Verify that Job Category search returns relevant job listings | Job Category "Business" | IE Browser | 1. Navigate to the serach jobs page 2. select "Business" from the job category drop down menu 3. Click on the search button | Only job listings under "Busness " category should be displayed | Only "Business" Jobs displayed successfully | Pass | Ensure that categories are accuratley populated
TC-JC-13 | Verify that Job Category search returns relevant job listings | Job Category "Programming" " | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Select "Programming" from the job category drop down menu 3. Click on the search button | Only job listings under "Programming" category should be displayed | "No Results Found" displayed successfully | Pass | This job category generated a "No Results Found" message
TC-JC-14 | Verify that Job Category search returns relevant job listings | Job Category "Programming" | IE Browser Browser | 1. Navigate to the serach jobs page 2. Select "Programming" from the job category drop down menu 3. Click on the search button | Only job listings under "Programming" category should be displayed | "No Results Found" displayed successfully | Pass | This job category generated a "No Results Found" message
TC-JC-15 | Verify that Job Category search returns relevant job listings | Job Category "Networking" | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Select "Networking" from the job category drop down menu 3. Click on the search button | Only job listings under "Networking" category should be displayed | Only "Networking" Jobs displayed successfully | Pass | Ensure that categories are accuratley populated
TC-JC-16 | Verify that Job Category search returns relevant job listings | Job Category "Networking" | IE Browser | 1. Navigate to the serach jobs page 2. Select "Networking" from the job category drop down menu 3. Click on the search button | Only job listings under "Networking" category should be displayed | Only "Networking" Jobs displayed successfully | Pass | Ensure that categories are accuratley populated
TC-JC-17 | Verify that Job Category search returns relevant job listings | Job Category "System Admin" | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Select "System Admin" from the job category drop down menu 3. Click on the search button | Only job listings under "System Admin" category should be displayed | Only "System Admin" Jobs displayed "No Results | Pass | This job category generated a "No Results Found" message
TC-JC-18 | Verify that Job Category search returns relevant job listings | Job Category "System Admin" | IE Browser | 1. Navigate to the serach jobs page 2. Select "System Admin" from the job category drop down menu 3. Click on the search button | Only job listings under "System Admin" category should be displayed | Only "System Admin" Jobs displayed "No Results Found" | Pass | This job category generated a "No Results Found" message
TC-JC-19 | Verify that Job Category search returns relevant job listings | Job Category "Administration" | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Select "Administration" from the job category drop down menu 3. Click on the search button | Only job listings under "Administration" category should be displayed | Only "Administration" Jobs displayed successfully | Pass | Ensure that categories are accuratley populated
TC-JC-20 | Verify that Job Category search returns relevant job listings | Job Category "Administration" | IE Browser | 1. Navigate to the serach jobs page 2. Select "Administration" from the job category drop down menu 3. Click on the search button | Only job listings under "Administration" category should be displayed | Only "Administration" Jobs displayed successfully | Pass | Ensure that categories are accuratley populated
TC-CN-21 | Verify that Company Name search returns relevant job listings | Enter Company Name Humana | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Type in the the company name "Humana"in the company name section 3. Click on the search button | Only job listings under the company name "Humana" should be displayed | Only company name "Humana" Jobs displayed successfully | Pass | Ensure that company name is accuratley populated
TC-CN-22 | Verify that Company Name search returns relevant job listings | Enter Company Name "Humana" | IE Browser | 1. Navigate to the serach jobs page 2. Type in the the company name "Humana"in the company name section 3. Click on the search button | Only job listings under the company name "Humana" should be displayed | Only company name "Humana" Jobs displayed successfully | Pass | Ensure that company name is accuratley populated
TC-PT-23 | Verify that position type "Full Time" search returns relevant job listings | Click on position type "fulltime " | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Click on fulltime in the position type section 3. Click on the search button | Only job listings under "full time" should be displayed | Only full time Jobs displayed successfully | Pass | Ensure that full time jobs are accuratley populated
TC-PT-24 | Verify that position type "Full Time" search returns relevant job listings | Click on position type "fulltime " | IE Browser | 1. Navigate to the serach jobs page 2. Click on fulltime in the position type section 3. Click on the search button | Only job listings under "full time" should be displayed | Only full time Jobs displayed successfully | Pass | Ensure that full time jobs are accuratley populated
TC-PT-25 | Verify that position type "Part Time" search returns relevant job listings | Click on position type "Part Time " | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Click on Part Time in the position type section 3. Click on the search button | Only job listings under "Part Time" should be displayed | Only Part Time Jobs displayed successfully | Pass | Ensure that Part Time jobs are accuratley populated
TC-PT-26 | Verify that position type "Part Time " search returns relevant job listings | Click on position type "Part Time" | IE Browser | 1. Navigate to the serach jobs page 2. Click on Part Time in the position type section 3. Click on the search button | Only job listings under "Part Time" should be displayed | Only Part Time Jobs displayed successfully | Pass | Ensure that Part Time jobs are accuratley populated
TC-PT-27 | Verify that position type "Contract W2 " search returns relevant job listings | Click on position type "Contract W2" | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Click on Contract W2 in the position type section 3. Click on the search button | Only job listings under "Contract W2" should be displayed | "No results found" message appears for Contract W2 | Pass | No results found messgage appears for Contract W2 jobs
TC-PT-28 | Verify that position type "Contract W2 " search returns relevant job listings | Click on position type "Contract W2" | IE Browser | 1. Navigate to the serach jobs page 2. Click on Contract W2 in the position type section 3. Click on the search button | Only job listings under "Contract W2" should be displayed | "No results found" message appears for Contract W2 | Pass | No results found messgage appears for Contract W2 jobs
TC-PT-29 | Verify that position type "Contract 1099 " search returns relevant job listings | Click on position type "Contract 1099" | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Click on Contract 1099 in the position type section 3. Click on the search button | Only job listings under "Contract 1099" should be displayed | "No results found" message appears for Contract 1099 | Pass | No results found messgage appears for Contract 1099 jobs
TC-PT-30 | Verify that position type "Contract 1099 " search returns relevant job listings | Click on position type "Contract 1099" | IE Browser | 1. Navigate to the serach jobs page 2. Click on Contract 1099 in the position type section 3. Click on the search button | Only job listings under "Contract 1099" should be displayed | "No results found" message appears for Contract 1099 | Pass | No results found messgage appears for Contract 1099 jobs
TC-JS-31 | Verify that job status type "Active" search returns relevant job listings | Click on "Active" under Job status | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Click on Active under Job Status category 3. Click on the search button | Only job listings under "Active " in the Job Status category should be displayed | Only Active Jobs displayed successfully | Pass | Ensure that Active jobs are accuratley populated
TC-JS-32 | Verify that job status type "Active" search returns relevant job listings | Click on "Active" under Job status | IE Browser | 1. Navigate to the serach jobs page 2. Click on Active under Job Status category 3. Click on the search button | Only job listings under "Active " in the Job Status category should be displayed | Only Active Jobs displayed successfully | Pass | Ensure that Active jobs are accuratley populated
TC-JS-33 | Verify that " Closed" under Job Status returns relevant job listings | Click on "Closed" under the Job Status category | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Click on "Closed" under the Job Status category 3. Click on the search button | Only job listings under "Closed " under Job Status category should be displayed | "No results found" message appears for "Closed" under the Joba Staus category | Pass | No results found messgage appears for "Closed" jobs
TC-JS-34 | Verify that " Closed" under Job Status returns relevant job listings | Click on "Closed" under the Job Status category | IE Browser | 1. Navigate to the serach jobs page 2. Click on "Closed" under the Job Status category 3. Click on the search button | Only job listings under "Closed " under Job Status category should be displayed | "No results found" message appears for "Closed" under the Joba Staus category | Pass | No results found messgage appears for "Closed" jobs
TC-JS-35 | Verify that " Hold" under Job Status returns relevant job listings | Click on "Hold" under the Job Status category | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Click on "Hold" under the Job Status category 3. Click on the search button | Only job listings under "Hold " under Job Status category should be displayed | "No results found" message appears for "Hold" under the Joba Staus category | Pass | No results found messgage appears for "Hold" jobs
TC-JS-36 | Verify that " Hold" under Job Status returns relevant job listings | Click on "Hold" under the Job Status category | IE Browser | 1. Navigate to the serach jobs page 2. Click on "Hold" under the Job Status category 3. Click on the search button | Only job listings under "Hold " under Job Status category should be displayed | "No results found" message appears for "Hold" under the Joba Staus category | Pass | No results found messgage appears for "Hold" jobs
TC-JS-37 | Verify that " Filled " under Job Status returns relevant job listings | Click on "Filled " under the Job Status category | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Click on "Filled" under the Job Status category 3. Click on the search button | Only job listings under "Filled " under Job Status category should be displayed | "No results found" message appears for "Filled" under the Joba Staus category | Pass | No results found messgage appears for "Filled" jobs
TC-JS-38 | Verify that " Filled " under Job Status returns relevant job listings | Click on "Filled " under the Job Status category | IE Browser | 1. Navigate to the serach jobs page 2. Click on "Filled" under the Job Status category 3. Click on the search button | Only job listings under "Filled " under Job Status category should be displayed | "No results found" message appears for "Filled" under the Joba Staus category | Pass | No results found messgage appears for "Filled" jobs
TC-JT-39 | Verify that Job Title "Quality Assurance" search returns relevant job listings | Type in Quality Assurance " in the Job Title section | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Type in Quality Assurance " in the Job Title section 3. Click on the search button | Only job listings under "Quality Assurance " in the Job Title category should be displayed | Only "Quality Assurance" Jobs displayed successfully | Pass | Ensure that Quality Assurance jobs are accuratley populated
TC-JT-41 | Verify that Job Title "Quality Assurance" search returns relevant job listings | Type in Quality Assurance " in the Job Title section | IE Browser | 1. Navigate to the serach jobs page 2. Type in Quality Assurance " in the Job Title section 3. Click on the search button | Only job listings under "Quality Assurance " in the Job Title category should be displayed | Only "Quality Assurance" Jobs displayed successfully | Pass | Ensure that Quality Assurance jobs are accuratley populated
TC-L-42 | Verify that Location "Illinois" search returns relevant jobs for selected location | Type in the location tab "Illinois" to locate jobs in that location | Google Chrome Browser | 1. Navigate to the serach jobs page 2. Type in "Illinois" in the Location Tab 3. Click on the search button | Only job listings in "Illinois " in the Location category should be displayed | Only jobs located in "Illinois" should displayed successfully | Pass | Ensure that entering the location will produce jobs are accuratley populated
TC-L-43 | Verify that Location "Illinois" search returns relevant jobs for selected location | Type in the location tab "Illinois" to locate jobs in that location | IE Browser | 1. Navigate to the serach jobs page 2. Type in "Illinois" in the Location Tab 3. Click on the search button | Only job listings in "Illinois " in the Location category should be displayed | Only jobs located in "Illinois" should displayed successfully | Pass | Ensure that entering the location will produce jobs are accuratley populated
TC-ER-44 | Verify that Educational Requirement "Bachelor Degree" search returns relevant job listings | Choose "Bachelors Degree" in the drop down in the Education Requirements Section | Google Chrome Browser | 1. Navigate to the serach jobs page 2.Choose "Bachelors Degree" from the drop down menu in the Education Requirements Section 3. Click on the search button | Only job listings under "Bachelors Degree " in the Educational Requirements section should be displayed | Only "Bachelors Degree" requirement displayed jobs successfully | Pass | Ensure that the educational requirement "Bachelors Degree" jobs are accuratley populated
TC-ER-45 | Verify that Educational Requirement "Bachelor Degree" search returns relevant job listings | Choose "Bachelors Degree" in the drop down in the Education Requirements Section | IE Browser | 1. Navigate to the serach jobs page 2.Choose "Bachelors Degree" from the drop down menu in the Education Requirements Section 3. Click on the search button | Only job listings under "Bachelors Degree " in the Educational Requirements section should be displayed | Only "Bachelors Degree" requirements displayed jobs successfully | Pass | Ensure that the educational requirement "Bachelors Degree" jobs are accuratley populated
TC-ER-46 | Verify that Educational Requirement "Master Degree" search returns relevant job listings | Choose "Master Degree" in the drop down in the Education Requirements Section | Google Chrome Browser | 1. Navigate to the serach jobs page 2.Choose "Masters Degree" from the drop down menu in the Education Requirements Section 3. Click on the search button | Only job listings under "Masters Degree " in the Educational Requirements section should be displayed | Only "Masters Degree" requirements displayed "No Results Found" message | Pass | Educational requirement "Masters Degree" jobs populates a "No Results Found" message
TC-ER-47 | Verify that Educational Requirement "Master Degree" search returns relevant job listings | Choose "Master Degree" in the drop down in the Education Requirements Section | IE Browser | 1. Navigate to the serach jobs page 2.Choose "Masters Degree" from the drop down menu in the Education Requirements Section 3. Click on the search button | Only job listings under "Masters Degree " in the Educational Requirements section should be displayed | Only "Masters Degree" requirements displayed "No Results Found" message | Pass | Educational requirement "Masters Degree" jobs populates a "No Results Found" message
TC-ER-48 | Verify that Educational Requirement "PHD Degree" search returns relevant job listings | Choose "PHD Degree" in the drop down in the Education Requirements Section | Google Chrome Browser | 1. Navigate to the serach jobs page 2.Choose "PHD Degree" from the drop down menu in the Education Requirements Section 3. Click on the search button | Only job listings under "PHD Degree " in the Educational Requirements section should be displayed | Only "PHD Degree" requirements displayed "No Results Found" message | Pass | Educational requirement "PHD Degree" jobs populates a "No Results Found" message
TC-ER-49 | Verify that Educational Requirement "PHD Degree" search returns relevant job listings | Choose "PHD Degree" in the drop down in the Education Requirements Section | IE Browser | 1. Navigate to the serach jobs page 2.Choose "PHD Degree" from the drop down menu in the Education Requirements Section 3. Click on the search button | Only job listings under "PHD Degree " in the Educational Requirements section should be displayed | Only "PHD Degree" requirements displayed "No Results Found" message | Pass | Educational requirement "PHD Degree" jobs populates a "No Results Found" message
TC-ER-50 | Verify that Educational Requirement "Associate Degree" search returns relevant job listings | Choose "Associate Degree" in the drop down in the Education Requirements Section | Google Chrome Browser | 1. Navigate to the serach jobs page 2.Choose "Associate Degree" from the drop down menu in the Education Requirements Section 3. Click on the search button | Only job listings under "Associate Degree " in the Educational Requirements section should be displayed | Only "Associate Degree" requirement displayed jobs successfully | Pass | Ensure that the educational requirement "Associate Degree" jobs are accuratley populated
TC-ER-51 | Verify that Educational Requirement "Associate Degree" search returns relevant job listings | Choose "Associate Degree" in the drop down in the Education Requirements Section | IE Browser | 1. Navigate to the serach jobs page 2.Choose "Associate Degree" from the drop down menu in the Education Requirements Section 3. Click on the search button | Only job listings under "Associate Degree " in the Educational Requirements section should be displayed | Only "Associate Degree" requirement displayed jobs successfully | Pass | Ensure that the educational requirement "Associate Degree" jobs are accuratley populated
TC-ER-52 | Verify that Educational Requirement "Other " search returns relevant job listings | Choose "Other" in the drop down in the Education Requirements Section | Google Chrome Browser | 1. Navigate to the serach jobs page 2.Choose "Other " from the drop down menu in the Education Requirements Section 3. Click on the search button | Only job listings under "Other " in the Educational Requirements section should be displayed | Only "Other " requirement displayed jobs successfully | Pass | Ensure that the educational requirement "Other " jobs are accuratley populated
TC-ER-53 | Verify that Educational Requirement "Other " search returns relevant job listings | Choose "Other" in the drop down in the Education Requirements Section | IE Browser | 1. Navigate to the serach jobs page 2.Choose "Other " from the drop down menu in the Education Requirements Section 3. Click on the search button | Only job listings under "Other " in the Educational Requirements section should be displayed | Only "Other " requirement displayed jobs successfully | Pass | Ensure that the educational requirement "Other " jobs are accuratley populated

## View Job
ID | Test Description | Test Data | Enviroment | Test Steps | Expected Result | Actual Result | Status | Comment
TC-VJ-01 | Verify that the specific job"Data Analyst" chosen displays the Job details | https://www.schaumburgmarketplace.net/jobs | Google Chrome Browser | 1. Navigate to the serach jobs page 2.Choose the Job "Data Analyst" 3. Click on View Job icon tab | When the View Job icon is chosen for "Data Analyst" the view job details page is displayed | Only the chosen Job "Data Analyst" will display a job details page once the "view job" icon is clicked on | Pass | Ensure that the View Job icon when clicked on will dispay a job detailspage for the chosen job "Data Analyst"
TC-VJ-02 | Verify that the specific job "Data & Reporting Business Analyst - Remotet" chosen displays the Job details | https://www.schaumburgmarketplace.net/jobs | IE Browser | 1. Navigate to the serach jobs page 2.Choose the Job "Data Analyst" 3. Click on View Job | When the View Job icon is chosen for "Data Analyst" the view job details page is displayed | Only the chosen Job "Data Analyst" will display a job details page once the "view job" icon is clicked on | Pass | Ensure that the View Job icon when clicked on will dispay a job details page for the chosen job "Data Analyst"
TC-VJ-03 | Verify that the specific job"Data Analyst" chosen displays the Job details | https://www.schaumburgmarketplace.net/jobs | Google Chrome Browser | 1. Navigate to the serach jobs page 2.Choose the Job "Data & Reporting Business Analyst - Remote" 3. Click on View Job icon tab | When the View Job icon is chosen for "Data & Reporting Business Analyst - Remote" the view job details page is displayed | Only the chosen Job "Data & Reporting Business Analyst - Remote" will display a job details page once the "view job" icon is clicked on | Pass | Ensure that the View Job icon when clicked on will dispay a job details page for the chosen job "Data & Reporting Business Analyst - Remote"
TC-VJ-04 | Verify that the specific job"Data Analyst" chosen displays the Job details | https://www.schaumburgmarketplace.net/jobs | IE Browser | 1. Navigate to the serach jobs page 2.Choose the Job "Data & Reporting Business Analyst - Remote" 3. Click on View Job icon tab | When the View Job icon is chosen for "Data & Reporting Business Analyst - Remote" the view job details page is displayed | Only the chosen Job "Data & Reporting Business Analyst - Remote" will display a job details page once the "view job" icon is clicked on | Pass | Ensure that the View Job icon when clicked on will dispay a job details page for the chosen job "Data & Reporting Business Analyst - Remote"

## Apply for Job
ID | Test Description | Test Data | Enviroment | Test Steps | Expected Result | Actual Result | Status | Comment
TC-AFJ-01 | Verify that within the View Job Detals Page for any chosen job the Apply for Job icon when clicked on will prompt the user to a separate page labeled "Application Login or Create Profile" | https://www.schaumburgmarketplace.net/jobs | Google Chrome Browser | 1..Action: Open the application or website and go to the page where jobs are listed. 2..Action: Click on any job listing to open its "View Job Details" page. 3..Action: On the "View Job Details" page, locate the "Apply for Job" icon. 4.Action: Click on the "Apply for Job" icon. 5..Action: Observe the page that appears after clicking "Apply for Job." 6..Action: Check for login fields and/or create profile options. | 1. Job listings should be displayed, with each job having a "View Job Details" option. Select a Job to View Details 2. The "View Job Details" page for the selected job should open, displaying details about the job. Locate the "Apply for Job" Icon 3. The "Apply for Job" icon should be visible and clickable. Click on the "Apply for Job" Icon 4. The system should navigate to a new page labeled "Application Login or Create Profile." Verify Navigation to "Application Login or Create Profile" Page 5. The new page should be labeled "Application Login or Create Profile" and should include options to log in or create a new profile. Confirm Functional Elements on the "Application Login or Create Profile" Page 6. Fields or options for logging in or creating a profile should be present and accessible. | Successful Navigation to "Application Login or Create Profile" Page: Actual Result: "After clicking the 'Apply for Job' icon, the user is directed to the 'Application Login or Create Profile' page, displaying login fields and options to create a new profile." | Pass | Since the actual result matches the expected outcome without any discrepancies, the test can be marked as a Pass. This confirms that the navigation flow and user interface elements for applying to a job are functioning correctly, providing a smooth experience for users attempting to apply.
TC-AFJ-01 | Verify that within the View Job Detals Page for any chosen job the Apply for Job icon when clicked on will prompt the user to a separate page labeled "Application Login or Create Profile" | https://www.schaumburgmarketplace.net/jobs | IE Browser | 1..Action: Open the application or website and go to the page where jobs are listed. 2..Action: Click on any job listing to open its "View Job Details" page. 3..Action: On the "View Job Details" page, locate the "Apply for Job" icon. 4.Action: Click on the "Apply for Job" icon. 5..Action: Observe the page that appears after clicking "Apply for Job." 6..Action: Check for login fields and/or create profile options. | 1. Job listings should be displayed, with each job having a "View Job Details" option. Select a Job to View Details 2. The "View Job Details" page for the selected job should open, displaying details about the job. Locate the "Apply for Job" Icon 3. The "Apply for Job" icon should be visible and clickable. Click on the "Apply for Job" Icon 4. The system should navigate to a new page labeled "Application Login or Create Profile." Verify Navigation to "Application Login or Create Profile" Page 5. The new page should be labeled "Application Login or Create Profile" and should include options to log in or create a new profile. Confirm Functional Elements on the "Application Login or Create Profile" Page 6. Fields or options for logging in or creating a profile should be present and accessible. | Successful Navigation to "Application Login or Create Profile" Page: Actual Result: "After clicking the 'Apply for Job' icon, the user is directed to the 'Application Login or Create Profile' page, displaying login fields and options to create a new profile." | Pass | Since the actual result matches the expected outcome without any discrepancies, the test can be marked as a Pass. This confirms that the navigation flow and user interface elements for applying to a job are functioning correctly, providing a smooth experience for users attempting to apply.

## Application Login Credentials
ID | Test Description | Test Data | Enviroment | Test Steps | Expected Result | Actual Result | Status | Comment
TC-LI-01 | Validate that users can log in by entering an email address and password or create an applicant profile by clicking the "Sign Up" button. | https://itexps.knack.com/ats#home/apply-for-job/671b986813b27c02d2cae66d/ | Google Chrome Browser and IE Browser | 1.Navigate to the "Sign in" or Create Account" page. 2.Enter a valid Email Address and Password from the test data for the login scenario. 3.Click on the Login button. 3. Repeat Steps 2-3 with an invalid Email Address or Password for the invalid login scenario. | Login Flow (Valid): -The user is successfully logged in and redirected to the application dashboard or homepage. Login Flow (Invalid): -The user is shown an error message indicating incorrect credentials (e.g., "Invalid email or password."). Forgot Password Flow: -The user is prompted to enter an email address. After submitting, a confirmation message appears, and a password reset email is sent to the specified email. Sign-Up Flow: The user is redirected to a new profile creation page or shown a form to complete profile details. | Login Flow (Valid): The user successfully logged in and was redirected to the application dashboard. Login Flow (Invalid): An error message was displayed: "Invalid email or password," as expected. Forgot Password Flow: The user was prompted to enter an email address. A confirmation message appeared after submission, and a password reset email was successfully sent. Sign-Up Flow: The user was redirected to the profile creation page and prompted to complete additional details for the new applicant profile. | Pass | User is able to login using current credentias or redirected to sign up for new account page when sign up tab is clicked on
TC-CAP-02 | Validate that a user can successfully create a profile by entering mandatory information, selecting options, and uploading documents. This test case covers all fields and drop-down selections in the "Create Profile" form. | https://itexps.knack.com/ats#home/apply-for-job/671b986813b27c02d2cae66d/ | Google Chrome Browser and IE Browser | 1.Navigate to the "Create Profile" page on the application. 2.Enter First Name and Last Name in the respective fields. 3.Enter a valid Email address. 4.Enter a secure Password and confirm it in the 5.Confirm Password field. 6.Enter a valid Phone number. 7.Fill in Street Address, Street Address 2, City, State, Zip, and Country fields. 8.Select Years of Experience from the dropdown menu. 9.Choose Interested Job Type, Job Preference, Apply For Job Position, and Availability from their respective dropdowns. 10.Select Yes for "Are you authorized to work in USA?". 11.Choose Immigration Status as "Citizen". Select Core Skills by choosing relevant skills from the options provided. 12.Enter a valid LinkedIn URL. 13.Select Highest Education level from the dropdown menu. 14.Upload a Resume document. 15.Upload a Cover Letter/Intro document. 16.Select Current Employment Status from the dropdown menu. 17.Enter Certifications and Training information as applicable. 18.Click on the Submit or Create Profile button to complete registration. | Upon clicking the Submit button: 1.A confirmation message should appear, indicating successful profile creation (e.g., "Your profile has been created successfully"). 2.User is redirected to their profile dashboard or the next appropriate page. 3.All entered details should be saved and displayed correctly on the user’s profile. | Profile Creation Successful: 1.A confirmation message appeared: "Your profile has been created successfully." 2.User was redirected to the profile dashboard, where all entered information was displayed accurately. 3.Uploaded resume and cover letter files were accessible and displayed under profile attachments. | Pass | All input fields, dropdown selections, and file uploads functioned as expected, with no issues encountered. The test was executed successfully, validating the complete profile creation process.

## Defect-AFJ
ID | Test Description | Test Data | Enviroment | Test Steps | Expected Result | Actual Result | Status | Comment
TC-AFJ-01 | Validate that clicking on the "Apply for Job" icon redirects the user to the correct page where they can enter credentials or sign up for an account. | https://www.schaumburgmarketplace.net/jobs | Google Chrome Browser | 1.Navigate to the job listing page. 2. Locate and click on the "Apply for Job" icon. | 1.User is redirected to the login/sign-up page. 2.Login or sign-up options are displayed correctly, allowing the user to either enter credentials or create an account if they do not have one. | User is redirected to a separate Knack Search Jobs page instead of the login or sign up for new account page within the original test data page | Fail | In order to sign in or sign up for new account the user must click on apply job within the view jobs page and even then will be redirected to a separate itexps.Knack.com page where the user can click on apply for job to sign in or sign up for a new account

## Edit Application Profile
ID | Test Description | Test Data | Enviroment | Test Steps | Expected Result | Actual Result | Status | Comment
TC-EAP-01 | Validate that a user can successfully edit and update fields in their application profile, ensuring changes are saved and reflected in the user’s profile. | https://itexps.knack.com/ats#edit-my-profile/ | Google Chrome and IE Browser | 1.Log into the application and navigate to the user profile dashboard. 2.Locate and click the Edit Profile button to access the profile editing page. 3.Update the First Name field with "Jonathan". 4.Update the Last Name field with "Smith". 5.Change the Email to "johndoe2024@example.com". 6.Update the Phone number to "(321) 654-0987". 7.Change Street Address to "456 New Street" and Street Address 2 to "Suite 10". 8.Update the City to "San Francisco" and Zip to "94105". 9.Select Years of Experience as "6". 10.Update Job Preference to "Onsite". 11.Change Availability to "2 Weeks Notice". 12.Modify Core Skills by adding "Python" and "SQL". 13.Update the LinkedIn URL to the new profile link. 14.Click the Save or Update Profile button to save changes. | After clicking the Submit button: 1.A confirmation message should appear, indicating "Profile updated successfully." 2.All updated information should be reflected on the profile page. 3.User should see the updated profile information when they navigate back to the profile dashboard. 4.No fields should revert to their original data after saving. | Profile Update Successful: 1.A confirmation message appeared: "Profile updated successfully." 2.All updated fields displayed the new information as entered. 3.The user profile dashboard showed the updated profile information when navigated back. 4.No fields reverted to their original data after saving. | Pass | The user was able to up date their profile information successfully

## View Apllication Profile
ID | Test Description | Test Data | Enviroment | Test Steps | Expected Result | Actual Result | Status | Comment
TC-VAP-01 | Validate that a user can successfully view their application profile, ensuring that all profile information is displayed correctly and accurately. | https://itexps.knack.com/ats#view-my-profile/ | Google Chrome and IE Browser | 1.Log into the application using valid credentials. 2.Navigate to the Profile section from the user dashboard or menu. 3.Click on the View Profile option to access the profile details page. 4.Verify that each section of the profile is displayed, including: -Personal Information: First Name, Last Name, Email, Phone, Address (Street, City, State, Zip, Country). -Professional Information: Years of Experience, Interested Job Type, Job Preference, Apply For Job Position, Availability, Authorized to Work in USA, Immigration Status. -Skills: Core Skills section with selected skills displayed. -Social and Additional Information: LinkedIn URL, Highest Education, Resume, Cover Letter/Intro, Current Employment Status, Certifications, and Training. 5.Confirm that all data is displayed exactly as it was entered during profile creation or last update. 6.Verify that uploaded files, such as Resume and Cover Letter, are accessible (e.g., with a link to download or view). 7. Check that the profile page layout is clear and all fields are labeled correctly. | User should be able to view the complete profile without any errors. All fields should display the correct information as per the saved profile details. Uploaded files, such as Resume and Cover Letter, should be accessible via links or buttons. Layout and labels should be clear and easy to read, with no broken links or missing information. | Profile View Successful: -User successfully accessed the profile page, and all sections were displayed without any errors. -All fields displayed correct information, exactly matching the saved profile details. -Uploaded Resume and Cover Letter were accessible through clickable links, allowing the user to view or download them. -The layout was clear, with all fields labeled correctly and visible without any formatting issues. | Pass | Profile view functionality worked as expected, confirming data integrity and accessibility across all profile sections.
TC-AAS-02 | Validate that a user can successfully add a new application by filling out the application form and submitting it. | https://itexps.knack.com/ats#home/apply-for-job/671b9ba6a9cb7f030ef2467e/ | Google Chrome and IE Browser | Log into the application using valid credentials.Click on View or edit application if needed Navigate to the Submit(button) Application section | After clicking the Submit button: A confirmation message should appear, indicating "Thank You! Your application has been submitted! Click on link below to view your Applications" The user should be redirected to the application summary page or dashboard. The newly added application details should be displayed correctly on the summary page. | Application Submission Successful: A confirmation message appeared: "Application submitted successfully." The user was redirected to the application summary page whe the Applications Tab is clicked on | Pass | The application submission functionality worked as expected, with all data accurately displayed and the submission process completed without any issues.